## Input
Sr. No. | Project_Code | Operator | Activity | Item_Description_Band | Site_Id | Site_Count | Pre_Done_Date | Post_Activity_Done_Date | Activity_Status | Remark | Report_Status | Report_Acceptance_Status | Client_Remark | Concatenate | Attempt_Cycle | Employee_Id | Employee_Name | Co_Ordinator
1 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R5009_TDD |  | 2018-04-02 | 2018-04-02 | Done |  |  |  |  | R5009_TDD-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
2 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 2357_TDD |  | 2018-04-09 | -620447 | Done |  |  |  |  | 2357_TDD-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
3 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 3128_TDD |  | 2018-04-03 | 2018-04-05 | Done |  |  |  |  | 3128_TDD-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
4 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 1405_TDD |  | 2018-04-04 | 2018-04-04 | Done |  |  |  |  | 1405_TDD-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
5 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 1428_TDD |  | 2018-04-04 |  | Partial Done |  |  |  |  | 1428_TDD-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
6 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 852_TDD |  | 2018-04-05 | 2018-04-05 | Done |  |  |  |  | 852_TDD-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
7 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 4065_TDD |  | 2018-04-05 | 2018-04-05 | Done |  |  |  |  | 4065_TDD-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
8 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 2412_GU |  | 2018-04-05 |  | Partial Done |  |  |  |  | 2412_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
9 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 1966_GU |  | 2018-04-05 | 2018-04-05 | Done |  |  |  |  | 1966_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
10 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 1963_GU |  | 2018-04-06 |  | Partial Done |  |  |  |  | 1963_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
11 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | DL_1451_MM |  | 2018-04-06 | 2018-04-06 | Done |  |  |  |  | DL_1451_MM-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
12 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | DL_R3339_MM |  | 2018-04-06 | 2018-04-06 | Done |  |  |  |  | DL_R3339_MM-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
13 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 763_GU |  | 2018-04-07 |  | Partial Done |  |  |  |  | 763_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
14 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | DL_6017_MM |  | 2018-04-18 | 2018-04-18 | Done |  |  |  |  | DL_6017_MM-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
15 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R244 |  | 2018-04-09 | 2018-04-09 | Done |  |  |  |  | R244-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
16 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R5984_TDD |  | 2018-04-09 | 2018-04-09 | Done |  |  |  |  | R5984_TDD-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
17 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 5279_GU |  | 2018-04-09 | 2018-04-09 | Done |  |  |  |  | 5279_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
18 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R5114 |  | 2018-04-10 |  | Partial Done |  |  |  |  | R5114-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
19 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R5063 |  | 2018-04-10 | 2018-04-10 | Done |  |  |  |  | R5063-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
20 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 3180_TDD |  | 2018-04-11 |  | Partial Done |  |  |  |  | 3180_TDD-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
21 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 5400_TDD |  | 2018-04-12 | 2018-04-12 | Done |  |  |  |  | 5400_TDD-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
22 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 5831_GU |  | 2018-04-13 |  | Partial Done |  |  |  |  | 5831_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
23 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 265_GU |  | 2018-04-14 | 2018-04-14 | Done |  |  |  |  | 265_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
24 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 1953_GU |  | 2018-04-16 |  | Partial Done |  |  |  |  | 1953_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
25 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 5928_GU |  | 2018-04-16 | 2018-04-16 | Done |  |  |  |  | 5928_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
26 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 5084_GU |  | 2018-04-17 | 2018-04-17 | Done |  |  |  |  | 5084_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
27 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R5697_GU |  | 2018-04-17 | 2018-04-17 | Done |  |  |  |  | R5697_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
28 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 2784_GU |  | 2018-04-19 | 2018-04-19 | Done |  |  |  |  | 2784_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
29 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 6212_GU |  | 2018-04-19 | 2018-04-19 | Done |  |  |  |  | 6212_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
30 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R331 |  | 2018-04-20 | 2018-04-20 | Done |  |  |  |  | R331-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
31 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R327 |  | 2018-04-20 | 2018-04-20 | Done |  |  |  |  | R327-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
32 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R4120 |  | 2018-04-20 | 2018-04-20 | Done |  |  |  |  | R4120-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
33 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R6076 |  | 2018-04-21 | 2018-04-21 | Done |  |  |  |  | R6076-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
34 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R2788 |  | 2018-04-21 | 2018-04-21 | Done |  |  |  |  | R2788-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
35 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R245 |  | 2018-04-23 | 2018-04-23 | Done |  |  |  |  | R245-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
36 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R266 |  | 2018-04-23 | 2018-04-23 | Done |  |  |  |  | R266-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
37 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R3866 |  | 2018-04-24 | 2018-04-24 | Done |  |  |  |  | R3866-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
38 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R2018 |  | 2018-04-24 | 2018-04-24 | Done |  |  |  |  | R2018-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
39 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R3238_GU |  | 2018-04-25 | 2018-04-25 | Done |  |  |  |  | R3238_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
40 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 5220 |  | 2018-04-25 | 2018-04-25 | Done |  |  |  |  | 5220-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
41 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 1364_GU |  | 2018-04-26 | 2018-04-26 | Done |  |  |  |  | 1364_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
42 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 5994_GU |  | 2018-04-26 | 2018-04-26 | Done |  |  |  |  | 5994_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
43 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 2233 |  | 2018-04-27 | 2018-04-27 | Done |  |  |  |  | 2233-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
44 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 2844 |  | 2018-04-27 | 2018-04-27 | Done |  |  |  |  | 2844-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
45 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R499 |  | 2018-04-27 | 2018-04-27 | Done |  |  |  |  | R499-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
46 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R2576 |  | 2018-05-04 | 2018-05-04 | Done |  |  |  |  | R2576-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
47 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 1534 |  | 2018-05-04 | 2018-05-04 | Done |  |  |  |  | 1534-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
48 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 1186_GU |  | 2018-05-05 | 2018-05-05 | Done |  |  |  |  | 1186_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
49 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 5799_GU |  | 2018-05-10 | 2018-05-10 | Done |  |  |  |  | 5799_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
50 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R1810 |  | 2018-05-10 | 2018-05-10 | Done |  |  |  |  | R1810-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
51 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 5155 |  | 2018-05-11 | 2018-05-11 | Done |  |  |  |  | 5155-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
52 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 1798_GU |  | 2018-05-12 | 2018-05-12 | Done |  |  |  |  | 1798_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
53 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 1965_GU |  | 2018-05-16 | 2018-05-16 | Done |  |  |  |  | 1965_GU-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
54 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 1496_TDD |  | 2018-05-26 | 2018-05-26 | Done |  |  |  |  | 1496_TDD-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
55 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 6149_DEL_TDD_N_RF |  | 2018-05-27 | 2018-05-27 | Done |  |  |  |  | 6149_DEL_TDD_N_RF-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
56 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 1179_DEL_TDD_N_RF |  | 2018-05-27 | 2018-05-27 | Done |  |  |  |  | 1179_DEL_TDD_N_RF-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
57 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 1830_DEL_TDD_N_RF |  | 2018-05-28 | 2018-05-28 | Done |  |  |  |  | 1830_DEL_TDD_N_RF-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
58 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | 3961_DEL_TDD_N_RF |  | 2018-05-30 | 2018-05-30 | Done |  |  |  |  | 3961_DEL_TDD_N_RF-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL
59 | HWDL | Hwaei | CUTOVER | SWAP Function Test service | R2756 |  | 2018-05-31 | 2018-05-31 | Done |  |  |  |  | R2756-SWAP Function Test service-CUTOVER | C2 | D1 | Site engineer 1 | John DL