## DPR
SN | PC | OPR | Activity | Item Description/Band | Site_id | Site Count | Month | Pre Done Date | Month | Post/Activity Done Date | Status | Remark for Attempt Issue and Pending Sites | Report Status | Report Acceptance Status | Remark | CONCATENATE | ATTEMPT CYCLE | EMP ID | Eng | PO Number | Ship Number | L1 Approval | L2 Approval | PO Value | Start Time | End Time | Advance | Approved | [7 empty] | Item Description | Activity
1 | HWKTK | VODA | CUTOVER | SWAP Function Test service | 1121_TDD | 1 | Apr | 2018-04-03 | Apr | 2018-04-05 | Attempt Issue | Power Off |  |  |  | 1121_TDD-SWAP Function Test service-CUTOVER | C1 | X | RAM | [9 empty] | X | RAM | Access Issue | Less Drive | Accepted | Submitted | Done | 8.4:RF coverage optimization without tools (LTE) (with CSFB+ Indoor Point Testing) | 4G-Cluster
2 | HWKTK | VODA | CUTOVER | SWAP Function Test service | 1121_TDD | 2 | Apr | 2018-04-04 | Jan |  | Done |  | Submitted | Rejected | Poor Throughput | 1121_TDD-SWAP Function Test service-CUTOVER | C2 | Y | Mohan | [9 empty] | Y | Mohan | Power Off | Poor Level | Rejected | Pending | Pending | 9.1:RF coverage optimization without tools (GSM/CDMA/EvDO) | 2G-Cluster
3 | HWKTK | VODA | 4G-Swap | 3.3:SWAP Drive test without tools (LTE)[SITE] | C | 3 | Apr | 2018-04-03 | Jan |  | Pending | Kit Issue |  |  |  | C-3.3:SWAP Drive test without tools (LTE)[SITE]-4G-Swap | C1 | Z | Sohan | [9 empty] | Z | Sohan | All Sector Not Serving | Poor Throughput | Validation Pending | Drive Not OK | Attempt Issue | 3.1:SWAP Drive test without tools (GSM/CDMA/EvDO)[SITE] | 2G-Swap
4 | HWKTK | VODA | 4G-Cluster | 9.3:RF coverage optimization without tools (LTE) | A |  | Apr | 2018-04-11 | Jan |  | Partial Done | Access Issue | Submitted | Accepted |  | A-9.3:RF coverage optimization without tools (LTE)-4G-Cluster | C1 | X | RAM | [9 empty] | Vendor Name | Surya | Kit Issue | Static |  |  | Partial Done | 3.3:SWAP Drive test without tools (LTE)[SITE] | 4G-Swap
5 | HWKTK | AIRTEL | 4G-Cluster | 9.3:RF coverage optimization without tools (LTE) | A |  | Jan |  | Jan |  | Done | Cab Issue | Pending | Pending |  | A-9.3:RF coverage optimization without tools (LTE)-4G-Cluster | C2 | Vendor Name | Surya | [9 empty] | X | RAM | Cab Issue | Others |  |  |  | 8.2:Single site verification without tools (UMTS/WIMAX) | 3G-SCFT
6 | HWKTK | AIRTEL | CUTOVER | SWAP Function Test service | 1121_TDD |  | Apr | 2018-04-11 |  |  | Done |  | Submitted | Accepted |  | 1121_TDD-SWAP Function Test service-CUTOVER | C3 | X | RAM | [9 empty] | X | RAM | Alarm on Site |  |  |  |  | 8.3:Single site verification without tools (LTE) | 4G-SCFT
7 | HWKTK | AIRTEL | 2G-Cluster | 9.1:RF coverage optimization without tools (GSM/CDMA/EvDO) | 1121_TDD | [5 empty] | Attempt Issue | Kit Issue |  |  |  | 1121_TDD-9.1:RF coverage optimization without tools (GSM/CDMA/EvDO)-2G-Cluster | C1 | Y | Mohan | [11 empty] | Infra Issue |  |  |  |  | SWAP Function Test service | CUTOVER
8 | HWKTK | AIRTEL | 3G-SCFT | 8.2:Single site verification without tools (UMTS/WIMAX) | 1121_TDD | [10 empty] | 1121_TDD-8.2:Single site verification without tools (UMTS/WIMAX)-3G-SCFT | C1 | X | RAM | [16 empty] | 9.3:RF coverage optimization without tools (LTE) | 4G-Cluster
9 | HWKTK | AIRTEL | 2G-Cluster | 9.1:RF coverage optimization without tools (GSM/CDMA/EvDO) | [11 empty] | -9.1:RF coverage optimization without tools (GSM/CDMA/EvDO)-2G-Cluster | C1 | X | RAM | [16 empty] | 3.2:SWAP Drive test without tools (UMTS/WIMAX)[SITE] | 3G-Swap
10 | HWUPW |  | - | [12 empty] | --- | C1 | Vendor Name | Surya | [16 empty] | 15.1:Technical testing (GSM/UMTS/LTE) without tool | MIMO
11 | HWUPW |  | - | [12 empty] | --- | C2 | X | RAM | [16 empty] | 8.1:Single site verification without tools (GSM/CDMA/EvDO) | 2G-SCFT
12 | HWUPW |  | - | [12 empty] | --- | C3 | [18 empty] | 9.2:RF coverage optimization without tools (UMTS/WIMAX) | 2G-Cluster
13 | HWUPW |  | - | [12 empty] | --- | C4 | [18 empty] | 18.5_Combo_ 9.1:RF coverage optimization without tools (GSM/CDMA/EvDO) + 9.3:RF coverage optimization without tools (LTE) | 2G/4G-Cluster
14 | HWUPW |  | - | [12 empty] | --- | C5 | [18 empty] | 18.11_Combo_ 8.1:Single site verification without tools (GSM/CDMA/EvDO) + 8.2:Single site verification without tools (UMTS/WIMAX) | 2G/3G-SCFT
15 |  |  | - | [12 empty] | --- | Critical | [18 empty] | 18.14_Combo_ 8.1:Single site verification without tools (GSM/CDMA/EvDO) + 8.2:Single site verification without tools (UMTS/WIMAX) + 8.3:Single site verification without tools (LTE) | 2G/3G/4G-SCFT
16 |  |  | - | [32 empty] | 19.6 LTE SCFT+VoLTE SCFT+CA Testing without Tool | LTE/VO/CA-SCFT-WOT
17 |  |  | - | [32 empty] | 19.8 VoLTE SCFT without Tool | VO-SCFT-WOT
18 |  |  | -
19 |  |  | -
20 |  |  | -

## Plan for FE
SN | Activity | Item Description | Site_id | Lat | Long | Need to Perform | Type | Engg. Location | Engg. Name | Advance | Approved |  | Item Description
1 | [11 empty] | FRESH | 8.4:RF coverage optimization without tools (LTE) (with CSFB+ Indoor Point Testing) | 4G-Cluster
2 | [11 empty] | REDRIVE | 9.1:RF coverage optimization without tools (GSM/CDMA/EvDO) | 2G-Cluster
3 | 4G-Swap | 3.3:SWAP Drive test without tools (LTE)[SITE] | A |  |  |  | REDRIVE | [5 empty] | 3.1:SWAP Drive test without tools (GSM/CDMA/EvDO)[SITE] | 2G-Swap
4 | [12 empty] | 3.3:SWAP Drive test without tools (LTE)[SITE] | 4G-Swap
5 | [12 empty] | 8.2:Single site verification without tools (UMTS/WIMAX) | 3G-SCFT
6 | [12 empty] | 8.3:Single site verification without tools (LTE) | 4G-SCFT
7 | [12 empty] | SWAP Function Test service | CUTOVER
8 | [12 empty] | 9.3:RF coverage optimization without tools (LTE) | 4G-Cluster
9 | [12 empty] | 3.2:SWAP Drive test without tools (UMTS/WIMAX)[SITE] | 3G-Swap
10 | [12 empty] | 15.1:Technical testing (GSM/UMTS/LTE) without tool | MIMO
11 | [12 empty] | 8.1:Single site verification without tools (GSM/CDMA/EvDO) | 2G-SCFT
12 | [12 empty] | 9.2:RF coverage optimization without tools (UMTS/WIMAX) | 2G-Cluster
13 | [12 empty] | 18.5_Combo_ 9.1:RF coverage optimization without tools (GSM/CDMA/EvDO) + 9.3:RF coverage optimization without tools (LTE) | 2G/4G-Cluster
14 | [12 empty] | 18.11_Combo_ 8.1:Single site verification without tools (GSM/CDMA/EvDO) + 8.2:Single site verification without tools (UMTS/WIMAX) | 2G/3G-SCFT
15 | [12 empty] | 18.14_Combo_ 8.1:Single site verification without tools (GSM/CDMA/EvDO) + 8.2:Single site verification without tools (UMTS/WIMAX) + 8.3:Single site verification without tools (LTE) | 2G/3G/4G-SCFT
16 | [12 empty] | 19.6 LTE SCFT+VoLTE SCFT+CA Testing without Tool | LTE/VO/CA-SCFT-WOT
17 | [12 empty] | 19.8 VoLTE SCFT without Tool | VO-SCFT-WOT
18
19
20

## Circle and Circle Code
DT-HUAWEI
SN | Bidding Packages | Circles | Circle Code FOR Huawei | Opratior
1 | SOUTH | KTK | HWKTK |  | Project Type
|  | Tamil Nadu & Chennai | HWTN |  | Site Basis
|  | Kerala | HWKL |  | Manmonth
|  | Andhra Pradesh | HWAP
2 | North | Haryana | HWHR
|  | Punjab | HWHP
|  | Rajasthan | HWRJ
|  | Delhi | HWDL
|  | UPE | HWUPE
|  | UPW | HWUPW
3 | East+WEST | Bihar & Jharkhand | HWBH
|  | Kolkata | HWKOL
|  | West Bengal | HWWB
|  | Orissa | HWOD
|  | Gujarat | HWGJ
|  | MPCG | HWMPCG
|  | Mumbai | HWMU
|  | Maharashtra | HWMH
Sub-Total

## Activity and Activity type
Item Description | Activity
8.4:RF coverage optimization without tools (LTE) (with CSFB+ Indoor Point Testing) | 4G-Cluster
9.1:RF coverage optimization without tools (GSM/CDMA/EvDO) | 2G-Cluster
3.1:SWAP Drive test without tools (GSM/CDMA/EvDO)[SITE] | 2G-Swap
3.3:SWAP Drive test without tools (LTE)[SITE] | 4G-Swap
8.2:Single site verification without tools (UMTS/WIMAX) | 3G-SCFT
8.3:Single site verification without tools (LTE) | 4G-SCFT
SWAP Function Test service | CUTOVER
9.3:RF coverage optimization without tools (LTE) | 4G-Cluster
3.2:SWAP Drive test without tools (UMTS/WIMAX)[SITE] | 3G-Swap
15.1:Technical testing (GSM/UMTS/LTE) without tool | MIMO
8.1:Single site verification without tools (GSM/CDMA/EvDO) | 2G-SCFT
9.2:RF coverage optimization without tools (UMTS/WIMAX) | 2G-Cluster
18.5_Combo_ 9.1:RF coverage optimization without tools (GSM/CDMA/EvDO) + 9.3:RF coverage optimization without tools (LTE) | 2G/4G-Cluster
18.11_Combo_ 8.1:Single site verification without tools (GSM/CDMA/EvDO) + 8.2:Single site verification without tools (UMTS/WIMAX) | 2G/3G-SCFT
18.14_Combo_ 8.1:Single site verification without tools (GSM/CDMA/EvDO) + 8.2:Single site verification without tools (UMTS/WIMAX) + 8.3:Single site verification without tools (LTE) | 2G/3G/4G-SCFT
19.6 LTE SCFT+VoLTE SCFT+CA Testing without Tool | LTE/VO/CA-SCFT-WOT
19.8 VoLTE SCFT without Tool | VO-SCFT-WOT

## Clint & Circle Details
PROJECT CODE | Customer name | Oprator
ERCAP | Huawei | Idea
HWBH | Nokia | Bharti
HWDL | ZTE | Jio
HWKOL | Ericsson | Vodafone
HWKTK | Samsung | MTS
NSNMH |  | BSNL
HWRJ
HWUPW
HWTN