## Sheet2
Sr.No. | Cab_Vendor_Name | Cab_Vendor_Type | Project_Code | Number_Of_Days | Amount | Total_Amount | Date

## 1527589778594
Project_Code | Operator | Activity | Item_Description_Band | Site_Id | Site_Count | Pre_Done_Month | Pre_Done_Date | Post_Activity_Done_Month | Post_Activity_Done_Date | Coordinator_Remark | Coordinator_Status | Report_Status | Report_Acceptance_Status | Client_Remark | Concatenate | Attempt_Cycle | Employee_Id | Employee_Name | Po_Number | Shippment_No | L1_Approval | L2_Approval | Po_Value | Start_Time | End_Time | Advance | Approved | Co_Ordinator
HWKTK | AIRTEL | 3G-SCFT | 8.2:Single site verification without tools (UMTS/WIMAX) | 1121_TDD | [10 empty] | 1121_TDD-8.2:Single site verification without tools (UMTS/WIMAX)-3G-SCFT | C1 | X | [10 empty] | Suraj
HWKTK | AIRTEL | 2G-Cluster | 9.1:RF coverage optimization without tools (GSM/CDMA/EvDO) | 1121_TDD | [5 empty] | Kit Issue | Attempt Issue |  |  |  | 1121_TDD-9.1:RF coverage optimization without tools (GSM/CDMA/EvDO)-2G-Cluster | C1 | Y | [10 empty] | Suraj
HWKTK | AIRTEL | CUTOVER | SWAP Function Test service | 1121_TDD |  | Apr | 2018-04-11 |  |  |  | Done | Submitted | Accepted |  | 1121_TDD-SWAP Function Test service-CUTOVER | C3 | X | [10 empty] | Suraj
HWKTK | AIRTEL | 4G-Cluster | 9.3:RF coverage optimization without tools (LTE) | A |  | Dec |  | Dec |  | Cab Issue | Done | Pending | Pending |  | A-9.3:RF coverage optimization without tools (LTE)-4G-Cluster | C2 | Vendor Name | [10 empty] | Suraj
HWKTK | VODA | 4G-Cluster | 3.3:RF coverage optimization without tools (LTE) | A |  | Apr | 2018-04-11 | Dec |  | Access Issue | Partial Done | Submitted | Accepted |  | A-9.3:RF coverage optimization without tools (LTE)-4G-Cluster | C1 | X | [10 empty] | Suraj
HWKTK | VODA | 4G-Swap | 3.3:SWAP Drive test without tools (LTE)[SITE] | C | 3 | Apr | 2018-04-03 | Dec |  | Kit Issue | Pending |  |  |  | C-3.3:SWAP Drive test without tools (LTE)[SITE]-4G-Swap | C1 | Z | [10 empty] | Suraj
HWKTK | VODA | CUTOVER | SWAP Function Test service | 1121_TDD | 2 | Apr | 2018-04-04 | Jan |  |  | Done | Submitted | Rejected | Poor Throughput | 1121_TDD-SWAP Function Test service-CUTOVER | C2 | Y | [10 empty] | Suraj
HWKTK | VODA | CUTOVER | SWAP Function Test service | 1121_TDD | 1 | Apr | 2018-04-03 | Apr | 2018-04-05 | Power Off | Attempt Issue |  |  |  | 1121_TDD-SWAP Function Test service-CUTOVER | C1 | X | RAM | [9 empty] | Suraj
8.2:Single site verification without tools (UMTS/WIMAX)
.

## Sheet1
Item_Description_Band
8.2:Single site verification without tools (UMTS/WIMAX)
9.1:RF coverage optimization without tools (GSM/CDMA/EvDO)
SWAP Function Test service
9.3:RF coverage optimization without tools (LTE)
9.3:RF coverage optimization without tools (LTE)
3.3:SWAP Drive test without tools (LTE)[SITE]
SWAP Function Test service
SWAP Function Test service